## 15-17
15-17 | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  |  | Project Planning Budget
Weeks | Activity | Percent Complete | Budgeted Cost for Work Scheduled (PV) | Budgeted Cost for Work Performed (EV) | Actual Cost for Work Performed (AC) | Cost Variance = 4-5 | Schedule Variance = 4-3 | Cost at completion | Cost to completion | Wks to Complete | Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | SUB | 9 | 10 | 11 | 12 | 13 | 14 | 15
7 | AB | 100% | 21000 | 21000 | 23500 | -2500 | 0 | 26297.619 | AB | 0 |  | 2009-07-03 | 2009-07-10 | 2009-07-17 | 2009-07-24 | 2009-07-31 | 2009-08-07 | 2009-08-14 | 2009-08-21 |  | 2009-08-28 | 2009-09-04 | 2009-09-11 | 2009-09-18 | 2009-09-25 | 2009-10-02 | 2009-10-09
10 | AC | 60% | 27000 | 18000 | 19200 | -1200 | -9000 | 20480 | AC | 4 | AB | 2000 | 2000 | 3000 | 3000 | 4000 | 4000 | 3000 |  | 21000 | [7 empty] | 0 | 21000
8 | AD | 88% | 32000 | 27280 | 37500 | -10220 | -4720 | 51548.7537 | AD |  | AC | 3000 | 3000 | 3000 | 4000 | 4000 | 4000 | 4000 | 2000 | 27000 | 2000 | 1000 | [5 empty] | 3000 | 30000
4 | BC | 50% | 3000 | 8500 | 8000 | 500 | 5500 | 7529.4118 | BC |  | AD | 5000 | 5000 | 6000 | 4000 | 4000 | 4000 | 3000 |  | 31000 | [7 empty] | 0 | 31000
2 | BE | 50% | 6000 | 6000 | 5500 | 500 | 0 | 5041.6667 | BE |  | BC | 2009-08-21: 4000 | 4000 | 4000 | 4000 | 5000 |  |  |  |  | 13000 | 17000
3 | CF | 0% | 0 | 0 |  | 0 | 0 | 0 |  | 3 | BE | 2009-08-21: 6000 | 6000 | 6000 | [6 empty] | 6000 | 12000
5 | DF | 0% | 0 | 0 |  | 0 | 0 | 0 |  |  | CF | [8 empty] | 0 |  |  |  | 2000 | 3000 | 3000 |  | 8000 | 8000
2 | EF | 0% | 0 | 0 |  | 0 | 0 | 0 |  |  | DF | [8 empty] | 0 |  | 3000 | 3000 | 4000 | 4000 |  |  | 14000 | 14000
1 | FG | 0% | 0 | 0 |  | 0 | 0 | 0 |  | 1 | EF | [8 empty] | 0 | 3000 |  | 2000 | 2000 |  |  |  | 7000 | 7000
|  |  | 89000 | 80780 | 93700 |  | -8220 | 110897.4511 | 17197.4511 | 8 | FG | [8 empty] | 0 | [6 empty] | 3000 | 3000 | 3000
[12 empty] | 10000 | 10000 | 12000 | 11000 | 12000 | 12000 | 10000 | 12000 | 89000 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 54000 | 143000
|  | Time to Completion= |  |  | Column 5
|  | Cost at completion = rate of spending X Total budget = |  |  | Column 4 | x ( ) =
[7 empty] | CPI | EV | 0.86211
|  | % Complete | Actual Cost | Week Remain | BCWP |  |  | AC
| AB | 100% | 23500 | 0
| AC | 60% | 19200 | 4 |  |  | SPI | EV | 0.90764 | [11 empty] | 2000 | 1000
| AD | 87.5% | 37500 | 1 |  |  |  | PV
| BC | 50% | 8000 | 2 | 143000 | labor & mat | [14 empty] | 4000 | 4000 | 5000
| BE | 50% | 5500 | 1 | 17000 | profit | [14 empty] | 6000
|  |  | 93700 |  | 160000 | Total | [17 empty] | 2000 | 3000 | 3000
[22 empty] | 3000 | 3000 | 4000 | 4000
| Original CP | [19 empty] | 3000 |  | 2000 | 2000
3000
|  |  | B7 | 7,9
|  | 0,7 |  |  | E2
|  |  |  | 7,11 | 9,11
Start | A |  | 0,10
|  |  |  | C10 | 11,14
|  |  | 0,8 |  |  |  | 14,15
|  |  |  | 8,13 |  | F | G
D8
At 8 weeks
[9 empty] | Orig CP | New CP
|  |  | B7 | 0,1
|  | 0,0 |  |  | E2 |  |  | AB | 7 | 8 |  | 2009-07-03: AC; 2009-07-10: Actual Cost
|  |  |  | 0,2 | 1,3 |  |  | AC | 10 | 12 |  | 2009-07-03: ACWP; 2009-07-10: Actual Cost of Work Performed
Start | A |  | 0,4 |  |  |  |  | AD | 8 | 8 |  | 2009-07-03: BAC; 2009-07-10: Budget At Completion
|  |  |  | C10 | 4,7 |  |  | BC | 4 | 8 |  | 2009-07-03: BCWP; 2009-07-10: Budgeted Cost of Work Performed
|  |  | 0,1 |  |  |  | 7,8 | BE | 2 | 8 |  | 2009-07-03: BCWS; 2009-07-10: Budgeted Cost of Work Scheduled
|  |  |  | 1,6 |  | F | G | CF | 3 |  |  | 2009-07-03: CV; 2009-07-10: Cost Variance
|  |  | D8 |  |  |  |  | DF | 5 |  |  | 2009-07-03: EAC; 2009-07-10: Estimate at Completion
[8 empty] | EF | 2 |  |  | 2009-07-03: EMV; 2009-07-10: Expected Monetary Value
[8 empty] | FG | 1 |  |  | 2009-07-03: ETC; 2009-07-10: Estimate to Complete
[12 empty] | EV | Earned Value
[12 empty] | PV | Planned Value
This worksheet demonstrates the tracking of schedule and cost using budget and actual numbers. On the current sheet, 15-17, activity resource utilization is work in process through row 7 of the worksheet. Column K, rows 3 to 12 give weeks to completion but are based solely on a linear work scope for that activity, (some work is light up front and heavy on the end). Budget variance is depicted with cost at completion in column I and has the same interpretive limitation as time to completion.

## 15-28 (hidden)
15-28 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Weeks | Activity | Percent Complete | Budgeted Cost for Work Scheduled (PV) | Budgeted Cost for Work Performed (EV) | Actual Cost for Work Performed (AC) | Cost Variance = 4-5 | Schedule Variance = 4-3 | Cost at completion (EAC) | Cost to completion
| A | 100% | 2000 | 2000 | 2000 | 0 | 0 | 2000
1 | B | 100% | 2000 | 2000 | 2400 | -400 | 0 | 2400
1 | C | 50% | 2000 | 1000 | 1000 | 0 | -1000 | 2000
1 | D | 0% | 0 | 0 | 0 | 0 | 0 | 0
1 |  | 62.5% | 6000 | 5000 | 5400 | -400 | -1000 | 8640 | 3240
|  | Time to Completion= |  |  | Column 5
|  | Cost at completion = rate of spending X Total budget = |  |  | Column 4 | x ( ) =
|  | BCWS: |  | 6000 |  | Project Planning Budget
|  | BCWP: |  | 5000 | Activity | 1 | 2 | 3 | 4
|  | ACWP: |  | 5400
2: BAC:; 4: 8640; 5: A; 6: 2000 |  |  | 2000
2: SV ($):; 4: -1000; 5: B; 7: 2000 |  |  | 2000
2: CV ($):; 4: -400; 5: C | 2000 |  | 2000
2: EAC =; 3: ([ACWP/BCWP]XBAC):; 4: 8640; 5: D |  | 2000 | 2000
2: ETC:; 4: 3240 |  |  | 8000 | BAC
|  | VAC: | VAC = BAC - EAC | 640
|  | % COMPLETE: |  | 62.5%
|  | % $$ SPENT |  | 67.5%
|  | CPI: | CPI = EV / AC | 0.92593 | Off | 0.95 | Gov. Stnd | 1.05
|  | SPI: | SPI = EV / PV | 0.83333 | Worse | 0.95 | Gov. Stnd | 1.05
|  | VAC= | BCWP | EV | 5000
|  |  | BAC | BAC | 8000
|  |  |  | AC | 5400
|  | % $$ SPENT= |  | BAC | 8000

## Sheet1
6 | 30 | 5
3 | 60 | 20
4 | 90 | 22.5
1 | 60000 | 60000